## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
E-mandi |  | 30 days | 2021-08-28 | 2021-09-28 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design | 2021-08-28 |  | 2 days
1.1 | Project Defination | 2021-08-28 | 2021-08-29 | 2 days
1.2 | Finish webpage | 2021-08-29 | 2021-09-01 | 4 days
1.3 | Project Design | 2021-09-02 | 2021-09-04 | 3 days
2 | Coding | 2021-09-05
2.1 | Phase 1 | 2021-09-05 | 2021-09-09 | 4 days
2.2 | Phase 2 | 2021-09-16 | 2021-09-18 | 3 days
2.3 | Additional Features | 2021-09-18 | 2021-09-19 | 2 days
3 | Testing | 2021-09-20
3.1 | Phase 1 Testing | 2021-09-20 | 2021-09-21 | 2 days
3.2 | Modification /Any changes | 2021-09-22 | 2021-09-22 | 1 day
3.3 | Phase 2 Testing | 2021-09-23 | 2021-09-23 | 1 day
3.4 | Modification /Any changes | 2021-09-24 | 2021-09-24 | 1 day
3.5 | Final Testing | 2021-09-25 | 2021-09-25 | 1 day
4 | Documentation | 27-09-2021 28-09-2021 |  | 2 days
4.1 | User Guide | 2021-09-28 | 2021-09-28 | 1 day
4.2 | Presentation | 2021-09-29 | 2021-09-29 | 1 day

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader
| Member Name | Sumit Sabbinwar
| PRN No | 210543181108
| Description | Front End(ReactJS+HTML+CSS)
2 | Role | Teammate
| Member Name | Omkar Dalvi
| PRN No | 210543181056
| Description | Back End (SpringBoot)
3 | Role | Teammate
| Member Name | Aditya Mohite
| PRN No | 210543181052
| Description | Back End (SpringBoot)
4 | Role | Teammate
| Member Name | Shraddha Kadam
| PRN No | 210543181103
| Description | Front End(ReactJS+HTML+CSS)